WHA Intranet Migration — Execution Runbook

Version 2 — rebuilt July 29, 2026 from the 7/21 runbook + the 7/29 review notes.  One phase per section; each phase starts on its own page.

How to use this runbook

Each phase is self-contained: open its page, confirm the 'Do not start until' line is satisfied, work the steps top to bottom, close the phase with its verification checklist. Phases 1 through 4 all run the same core loop below on different sites — the loop is printed once and referenced from each phase rather than repeated.

Files this runbook leans on: 2026-07-27_RootSubSite-SizeAudit.xlsx (the size source of truth — the July worksheet's size column is stale for IT&HIM, whasites and train), WHA_Subsite_Migration_Worksheet_v2.xlsx (per-site data, wave assignments, status tracking — refresh its sizes from the 7/27 audit), and analysis/fix-lists/ (one CSV per site listing every location that links TO that site, plus wave5-links-to-root-libraries.csv for Phase 5).

What changed in v2 (July 29)

1.  Sizes refreshed from the 7/27 audit throughout — including the full site inventory table on the next page, added so wave assignments can be argued from data.

2.  IT & HIM confirmed at 35 GB (unused backup cleaned up — was 1.19 TB). Phase 5b retired — IT moves first instead (item 6). The pre-production stress test retargets to Training.

3.  Training gets the careful treatment: background bulk pre-copy + incremental passes, ratified 7/29. It is now the largest copy job in the project and a busy, live site.

4.  The 7/29 review notes are integrated in place: green = ratified change, yellow = review note carried forward, red = decision the team still owes.

5.  Access policy closed (Gary, 7/29): once a site is moved, access to the old site is removed. Every old link fails except the main page, which shows the 'this site has moved' notice. The stub standard and the deep-links language are rewritten to match — the old read-only default is gone.

6.  IT moves first (Gary, 7/29): IT & HIM — renamed IT — becomes Pilot A, ahead of PFS. Phase 5b is retired; its surviving tasks ride with the pilot.

Open decisions on the table (as of 7/29)

D-A  IT rename + pilot slot — direction set 7/29, confirm Monday. Gary's call: rename IT & HIM to IT (/sites/IT) and move it FIRST, as Pilot A. Name must be final before the move — destination URL, nav labels and fix-list mapping all hang off it. IT-Internal folds into the IT site in Phase 8 either way.

D-B  zzRootBackup — method DECIDED 7/29: ShareGate copy. Pristine Copy Structure and Content → zzRootBackup/<site> BEFORE the moved-notice page and access change touch the source. With access-off now policy, the backup is the recovery path for every post-move 'I need that old file' request — and the retention record that is ours to control. Still open with Compliance: retention length, and is a frozen copy enough?

D-C  Scheduled re-enable of custom scripts for redirects. Proposal from the 7/29 notes. It does not remove the failure risk — it moves it to 'did the task run', and every stub dies at the swap anyway. Decide whether the cleverness earns its audit burden.

D-D  Interim hub on the classic root before cutover. For search/nav benefits during the migration window. Caveat the notes gloss over: hub nav renders only on modern pages — the classic root home page itself will not show it. Sequence if adopted: disassociate + unregister before the swap, re-register the new root after.

D-E  Reconcile /HIM vs /HIMCommittee. The STS#3 subsite at /HIM appears in both the Phase-2 committee group and the Decision-4 review list; the worksheet records its URL incorrectly as /himcommittee. Pick its lane.

D-F  People Search / EmployeeDirectoryPro. Suggestion on the table: postpone as its own project rather than solving it inside Phase 6.

Also noted: build the Decision Log once this plan is finalized; Document Hub libraries can be scaffolded now (content still waits for Phase 8).

Site inventory — every subsite, sized and placed

Sizes from 2026-07-27_RootSubSite-SizeAudit.xlsx; link counts from the 7/17 tenant scan (verified 7/20); dispositions from the migration worksheet. Red rows carry an open question or a changed fact. Every site moves AS-IS first; the 'After cutover' column is the Phase-8 transformation, deliberately deferred.

Reading the table: 'Inbound' = links from elsewhere in the tenant that break when this site moves (nav counts shown separately — they are the fast fixes). 'Self' = links inside the site that ShareGate's link correction rewrites during the copy. Twenty sites have zero inbound links — their move order is genuinely free.

| Phase | Site (full name) | URL | Size (7/27) | Inbound | Self | After cutover (Phase 8 disposition) | Flags / notes for the move discussion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1-A pilot | IT & HIM Department → IT | /IT&HIM | 35.1 GB | 6 (3 nav) | 0 | Standalone — renamed IT (/sites/IT) | MOVES FIRST (decided 7/29): the technical pilot, on IT's own site where breakage is cheap. 35 GB confirmed 7/27 after backup cleanup (was 1.19 TB); Phase 5b retired. Name final before move (D-A). Legacy URL '&' → %26 in scripts. Retention sign-off before old-subsite deletion. |
| 1-B pilot | Patient Financial Services | /PFS | 5.0 GB | 2 (1 nav) | 4 | Standalone — PFS / Revenue Cycle site | The department rehearsal: real users, real comms, distinct owner and audience, only 2 inbound links. Proves the human loop the IT pilot can't. (Was 4.7 GB on the July worksheet; 5.0 GB on the 7/27 audit.) |
| 2 | Committees (umbrella) | /Committees | 177 MB | 2 | 35 | Teams — per-committee channels (Ph 8) | Carries 11 outbound links to other sites (mostly HR) — those sit on HR's inbound fix list, not this move. |
| 2 | Interiors Committee | /Int | 66 MB | 0 | 4 | Teams channel (Ph 8) | Straightforward zero-inbound move. |
| 2 | Compensation Committee | /Comp | 6.8 MB | 0 | 4 | Private Teams channel (Ph 8) | Sensitive content — verify restricted permissions land intact at the destination. |
| 2 | Finance Committee | /Fin | 4.0 MB | 0 | 4 | Private Teams channel (Ph 8) | Sensitive content — same permission verification as Comp. |
| 2 | Operations Committee | /Ops | 4.6 MB | 0 | 8 | Teams channel (Ph 8) |  |
| 2 | Patient Focus Team Care | /PFTC | 1.1 MB | 0 | 4 | Teams channel (Ph 8) |  |
| 2 | Recruitment Committee | /RecruitmentCommittee | 0.4 MB | 0 | 4 | Teams channel under HR (Ph 8) |  |
| 2 | Information Security | /IS | 0.6 MB | 0 | 4 | Fold into IT site or Compliance site (Ph 8) | Tiny. |
| 2 ? | HIM Committee (subsite) | /HIM | 13 MB | 0 | 4 | Teams channel (Ph 8) | RECONCILE: appears in both the Phase-2 committee group and the Decision-4 review list. Worksheet records its URL as /himcommittee; the tenant URL is /HIM. Distinct from the deprecated /HIMCommittee meeting workspace below. |
| 2 | Forms | /Forms | 289 MB | 1 (1 nav) | 3 | Doc Hub — Consents / Patient Forms (Ph 8) | Content, not a site. Moves as-is now; Hub routing later. |
| 2 | Clinician Resource Library | /CRL | 7.2 MB | 0 | 4 | Doc Hub clinical pages (Ph 8) | Merges with Clinician Resources content in Phase 8. |
| 2 | Clinician Resources | /ClinicianResources | 0.6 MB | 0 | 4 | Doc Hub clinical pages (Ph 8) | Twin of CRL — same Phase-8 destination. |
| 2 | Ctrl+Alt+Delight Newsletter | /CtrlAltDelight_Newsletter | 0.3 MB | 0 | 4 | Hub News posts; back catalog archived (Ph 8) |  |
| rider | Weekly EMR Meeting | /EMRWeeklyMeeting | 0.5 MB | 0 | 0 | Rider — archives with the root at the swap | Deprecated MPS#0 Meeting Workspace — SPO cannot create a 1:1 destination. Zero links, <0.5 MB. Stays retrievable from the archive. |
| rider | HIM Committee (Meeting Workspace) | /HIMCommittee | 0.4 MB | 0 | 0 | Rider — archives with the root at the swap | Deprecated MPS#0. Duplicate of /HIM above — extract anything worth keeping, then let it ride. |
| 3 | Accounting | /Accounting | 706 MB | 10 (1 nav) | 15 | Standalone — Finance/Accounting site | Sources: root, CS, Forms. Committee content stays separate (Teams). Standard core loop. |
| 3 | Safety | /Safety | 23.3 GB | 5 (1 nav) | 531 | Merge → Compliance site with QI + HIPAA (Ph 8) | 531 self links — verify with a 30+ spot-check sample. SDS Inventory workbook holds 462 of 808 document-link occurrences — find-and-replace pass right after the move; backup before access is cut. Moves in one window with QI + hipaa. |
| 3 | Quality Improvement | /QI | 184 MB | 8 (2 nav) | 23 | Merge → Compliance site (Ph 8) | Same window as Safety and hipaa so their mutual links get fixed once. |
| 3 | HIPAA | /hipaa | 17.9 MB | 2 (1 nav) | 2 | Merge → Compliance site (Ph 8) | Same window as Safety and QI. |
| 3 | Help Desk Self-Service Portal | /HelpDeskSelfServicePortal | 164 MB | 3 | 312 | Page on IT site, or retire (Ph 8 call) | 312 of 318 findings are the same templated newsletter self-reference — they rewrite in the copy. |
| 3 | IT Internal | /IT-Internal | 6.2 MB | 0 | 5 | Fold into IT site (Ph 8) | As-is move now. A rename of IT&HIM to 'IT' makes this fold-in cleaner. |
| 3 gate | WHA Sites | /whasites | 7.6 GB | 6 (4 nav) | 106 | Review — TBD (Decision 4) | Size HALVED since the July 6 worksheet (14.9 → 7.6 GB) — confirm what was removed and by whom. Purpose still unclear from inventory. |
| 3 gate | Central Park Documents & Forms | /whaiis01 | 2.2 GB | 1 (1 nav) | 3 | Doc Hub content via inventory categories (Ph 8) | Content, not a site. Decision 4: move as-is now or accepted rider. |
| 3 gate | LLC Members | /LLCM | 102 MB | 0 | 4 | Review — private/restricted site (Decision 4) | Physician partners? Needs restricted access — confirm audience and owner. |
| 3 gate | The Patient Experience | /TPE | 24.7 MB | 0 | 3 | Review — Teams or Doc Hub content (Decision 4) |  |
| 3 gate | Legacy Sharing | /LegacySharing | 19.6 MB | 0 | 13 | Review / Archive (Decision 4) | Name suggests external sharing — audit permissions and sharing links before deciding. |
| 3 gate | Private | /Private | 4.1 MB | 0 | 4 | Review — TBD (Decision 4) | Name is a red flag — audit content and permissions first. |
| 3 gate | Strategic Plan | /SP | 1.1 MB | 0 | 4 | Review — leadership site/Teams (Decision 4) | Leadership-only audience — confirm owner. |
| 4 | Training | /train | 259.4 GB | 25 (1 nav) | 162 | Standalone — Training site + backend library | NOW THE LARGEST COPY JOB IN THE PROJECT (57% of subsite content) and a busy, live site. Changed 7/29: background bulk pre-copy during Phases 2–3 + incremental passes; Phase-4 window handles only the final delta + a short freeze. Training library owner question still open. |
| 4 | Human Resources | /HR | 46.8 GB | 72 (9 nav) | 194 | Standalone — HR site + backend library | Heaviest inbound target in the tenant (train 13, Committees 11, Epic 10, root 8). Goes late in the window, once the team is warmed up. 54 sharing links to regenerate. |
| 4 | Clinicians | /Clinicians | 70.0 GB | 13 (2 nav) | 42 | Merge → Clinical Services (Ph 8) | Third-largest site. Moves as-is in the same window as CS; the merge itself waits for Phase 8. |
| 4 | Clinical Services | /CS | 3.4 GB | 53 (1 nav) | 29 | Standalone — merge target for Clinicians | 28 of its 53 inbound links come from the root. 41 sharing links. |
| 4 | Epic | /Epic | 1.7 GB | 37 (1 nav) | 72 | Merge target — emr folds in (Ph 8) | 21 of 37 inbound links come from /train — the reason these move in one window. |
| 4 | EMR | /emr | 1.9 MB | 0 | 8 | Merge → Epic (Ph 8) | Zero inbound; rides the Phase-4 window so the Epic pairing lands together. |
| 5 | Root — WHA SharePoint (Central Park) | / | 1,380 GB * | 607 root-library links | — | Libraries out to standalone sites; classic root goes read-only, then swaps (Ph 6) | * Collection-level number — includes subsites plus recycle bins, likely still counting the deleted IT&HIM backup; purge + re-audit rides with Pilot A. All Provider Meetings (317 links, weekly uploads) and COVID19 (107) are the most-linked content in the tenant. |

ShareGate task definitions

Duplicate Site Collection — full collection copy.   Copy Structure and Content — one subsite → destination.   Copy Content — content only (rarely used).   Promote Subsite into Site — subsite → own site collection.

Pre-production validation — before Phase 1

☐  Test 1 — Full Duplicate Site Collection (root + subsites). Why: surfaces breakage early, timing data. Confirm: Site Contents, permissions, links, timing.

☐  Test 2 — Bulk copy of /train to a staging site. Why: train is now the project's largest copy job (259 GB) and a busy live site — this test produces the throttling/timing data the Phase-4 plan depends on, and validates the background-copy + incremental workflow before it matters.

Changed 7/29:  Test 2 retargeted from 'Promote IT&HIM (biggest site)' — IT&HIM is 35 GB after cleanup and no longer stresses anything. Training is where scale risk now lives.

Neither test touches the source — safe anytime. Gate: both tests done before Phase 1.

The core loop — run for every site in Phases 1–4

T minus 1 week

☐  Confirm destination. New URL under /sites/<name> per the naming convention; owner named; permissions model agreed. Nearly every subsite has broken inheritance — unique permissions get re-created deliberately at the destination, never assumed (we verify, we don't trust blindly). Permissions are carried over as-is, not stripped. AD security groups keep working.

☐  Pull the fix list. analysis/fix-lists/inbound-to-<site>.csv — every location in the tenant that links to this site. Notify the owner of each SOURCE site on the list.

☐  Record the mapping. Old URL → new URL goes in the worksheet row; announce the cutover window and read-only freeze to the site's users.

Move day

☐  Freeze. Set the source subsite read-only.

☐  Back up — zzRootBackup (added 7/29; method: ShareGate copy, decided 7/29). Copy Structure and Content → zzRootBackup/<site> BEFORE anything alters the source — the moved-notice page, the access change. This pristine copy is the retention record (ours to control, unlike whatever rides to the archive at the swap) and the recovery path for any post-move 'I need that old file' request.

Note (7/29 review):  Copy and Promote run simultaneously without conflict; the backup also surfaces Promote's issues early, and doubles as the compliance retention record.

☐  Copy. ShareGate migration with link correction enabled — that fixes links WITHIN the site, not outbound ones. Verify item counts and permissions at the destination before declaring the copy good.

☐  Nav. Update navigation entries pointing at the old URL — fix-list rows with ItemType 'Navigation'. Most live on the classic home page Quick Launch; patch them to the new /sites/ URL (patched links survive the eventual root swap unchanged).

☐  Stub. Convert the old subsite into a stub per the stub standard below.

The stub standard

☐  The old subsite IS the stub — and it goes dark. ShareGate copies, it doesn't delete — so after the copy is verified: replace the subsite home page with a single modern page ('This site has moved' banner + one large button to the new /sites/ URL + a contact line), then REMOVE STAFF ACCESS to everything else on the old site. The notice page is the only thing anyone can still reach. ~10 minutes per site.

Changed 7/29:  Access policy closed 7/29 (Gary) — supersedes the read-only default in earlier drafts. Once a site is moved, old links fail fast, by design: a dead link beats a stale policy or clinical workflow. Retention is not the stub's job — zzRootBackup, captured before the access change, is the recovery record. Side benefit: the old copies drop out of staff search immediately (security trimming).

☐  No stale-read exceptions to manage. Because access is off everywhere, there is no per-library triage, no move-day emptying of 'dangerous' libraries, and no data-loss risk from doing that emptying wrong. The old exception process is retired; the default covers everything.

☐  No auto-redirect scripting. Meta-refresh/JavaScript redirects require the custom-script setting, which Microsoft auto-reverts every 24 hours — they silently die. One honest extra click beats a clever redirect nobody is watching.

Note (7/29 review):  Proposal on the table (D-C): a scheduled job re-enabling custom scripts more than once per 24h — already done daily for ShareGate, so no new overhead. If used for redirects: keep a tracking sheet and phase them out near cutover. It doesn't remove the fail risk, it moves it to 'did the task run'.

☐  Stub lifetime — the honest limit. Stubs are subsites of the old root, so they ride to the archive at the swap and the old paths become plain 404s — even the notice page dies then. Real stub coverage = from each site's move until swap day. This is why the pre-swap buffer is weeks, not days (Phase 6), and why every move announcement teaches people to fix their own bookmarks.

T plus 1 week

☐  Work the fix list. Pages and list items first — fast find-and-replace. Then documents per the Decision 2 fix-forward policy. Sharing links (/:x:, /:b: style — flagged IsSharingLink) cannot be edited; regenerate them as direct URLs.

Note (7/29 review):  The fix workload is rolling and compounding — each wave's list covers the current site plus everything already moved; ShareGate can't predict our order. Tooling: manual + PowerShell pattern-match, still TBD.

☐  Spot-check ShareGate's work. Sample 10–15 links inside the moved site; link correction is 'likely fixed', not guaranteed.

☐  Re-scan. Run the link scanner scoped to the moved site's OLD url; expect zero live references outside documents you've decided not to fix. Attach the result to the worksheet row and set Status.

PHASE 1 — Two pilots — IT first, then PFS

When: First moves; set the tempo for everything after ¦ Who: IT (Gary) for Pilot A; IT + PFS site owner for Pilot B ¦ Do not start until: ShareGate licensed and configured; core loop agreed; pre-production tests done; IT rename final (D-A)

Changed 7/29:  Decided 7/29: IT & HIM — renamed IT — moves FIRST, as Pilot A. It was parked in Phase 5b back when it was 1.19 TB; at a confirmed 35 GB with 6 inbound links there is no reason to wait, and piloting on our own site means the mistakes land on the most forgiving audience in the building. Phase 5b is retired; its surviving tasks ride with this pilot.

Pilot A — IT (35 GB, 6 inbound links, 3 nav): the technical pilot. Validates the rename, zzRootBackup, the copy, the access-off stub and the fix loop — where breakage costs nothing.

Pilot B — PFS (5.0 GB, 2 inbound links): the department rehearsal. Real users, real comms, distinct owner and audience — it proves the human loop Pilot A can't: announcements, freeze, moved-notice, first-week tickets.

Run — Pilot A (IT)

☐  Close the name first. IT (/sites/IT) per Gary's 7/29 direction — confirm with governance Monday, then it's frozen: destination URL, nav label, comms and fix-list mapping all hang off it.

☐  Execute the core loop end to end on IT. First live test of the backup step: confirm zzRootBackup completes AND verifies before the notice page and access change touch the source. HIM content may carry records-retention requirements — get HIM/Compliance sign-off before the old-subsite deletion below. Fix its 6 inbound links (3 nav; sources: HelpDeskSelfServicePortal, root, HR, train). Remember %26 wherever the old URL appears in scripts.

☐  Housekeeping that rides along: purge both recycle-bin stages left by July's backup cleanup, re-run the size audit, and re-baseline tenant storage — the current root row (1,380 GB) likely still counts the deleted backup. Then, after verification + retention sign-off: delete the old /IT&HIM subsite (before the swap either way, so the archive doesn't carry a duplicate).

Run — Pilot B (PFS)

☐  Execute the core loop end to end on PFS. No shortcuts — the point is to validate the loop as a department experiences it, not the site.

☐  Draft the standard user comms from what PFS users actually asked.

☐  Time every step in BOTH pilots (copy duration, fix-list minutes, verification) and note surprises directly in the worksheet rows.

Close the phase when

☐  IT staff are working on the new IT site and PFS users on theirs, with zero open tickets for a full week.

☐  All eight fix-list items (6 IT + 2 PFS) are closed and both scoped re-scans are clean.

☐  The old /IT&HIM subsite is deleted (post-verification, post-retention-sign-off) and the storage re-baseline is recorded.

☐  The team has reviewed the timings and amended the core loop where reality disagreed with the plan.

PHASE 2 — Zero-inbound movers — as-is, 1:1

When: Immediately after pilot sign-off; parallelize freely ¦ Who: IT, with site owners ¦ Do not start until: Phase 1 closed

Every site in this phase has ~zero inbound links — nothing else in the tenant breaks when it moves, so these can run in any order, several per week. Each subsite becomes its OWN standalone site under /sites/, content untouched: no merges, no Teams conversion, no Document Hub routing. All of that is Phase 8, after cutover.

Sites (each → its own /sites/<name>, as-is)

Committee sites: Committees (umbrella), Int, Comp, Fin, Ops, PFTC, RecruitmentCommittee, IS — plus /HIM pending D-E. Comp and Fin hold sensitive content — verify restricted permissions land intact.

Doc-Hub-bound content (later): Forms, CRL, ClinicianResources, CtrlAltDelight_Newsletter. Move as-is now to their own sites; Hub routing is Phase 8. Nothing here waits on the Hub.

The one exception: EMRWeeklyMeeting and HIMCommittee (deprecated MPS#0 Meeting Workspaces) cannot move as-is — SPO can no longer create Meeting Workspace sites. Zero links point at them and both are under 0.5 MB: leave them as riders; they archive with the root in Phase 6 and stay retrievable.

Notes

☐  Committees has 11 outbound links pointing at other sites (mostly HR) — those are on HR's inbound fix list, not this phase's problem.

☐  Run the core loop's verification even here — 'no inbound links' is the scan's claim; the re-scan confirms it.

☐  Start the Training background bulk copy during this phase (changed 7/29 — see Phase 4). At 259 GB it is now the longest-running job in the project; it should be grinding away while the small moves happen. Verify tenant storage headroom against the re-baselined numbers from Pilot A's recycle-bin purge.

Note (7/29 review):  Backup-before-access-off applies here too — don't skip zzRootBackup because these are small sites.

Close the phase when

☐  All Phase-2 rows in the worksheet show Complete, each with a clean scoped re-scan; the two workspace riders are recorded as accepted riders.

PHASE 3 — Modest inbound — as-is, 1:1

When: After Phase 2; 2–3 weeks ¦ Who: IT + site owners ¦ Do not start until: Phase 2 closed

Moves (each → its own /sites/<name>, as-is)

☐  Accounting. 10 inbound links (9 pages/lists, 1 nav — sources: root, CS, Forms). Standard core loop.

☐  Safety, QI, hipaa — three separate sites, ONE window. No merging (that's Phase 8) — but they link to each other, so one window means their mutual links get fixed once. Combined inbound: 15. Safety alone carries 531 self links; ShareGate rewrites those during the copy — verify with a bigger spot-check sample (30+).

Note (7/29 review):  Safety's SDS Inventory workbook alone holds 462 of the 808 document-link occurrences in the tenant — schedule its find-and-replace pass immediately after the move, and confirm the zzRootBackup capture lands before access is cut.

☐  HelpDeskSelfServicePortal. Moves as-is to its own site (312 of 318 findings are the same templated newsletter reference — self links rewrite in the copy). 3 inbound links. Whether it later becomes a page on the IT site is a Phase 8 call.

☐  IT-Internal. 5 self links, zero inbound. As-is move.

Also due in this phase

☐  Decision-4 confirmations should be landing now: TPE, LegacySharing, Private, SP, LLCM, whasites, HIM (see D-E), whaiis01 — each either moves as-is in this phase or is recorded as an accepted rider that archives with the root in Phase 6.

Note (7/29 review):  whasites halved in size since July 6 (14.9 → 7.6 GB) — confirm what was removed and by whom before deciding its disposition.

Close the phase when

☐  Accounting, Safety, QI, hipaa, Help Desk, IT-Internal live on their own sites with their 28 combined inbound links closed; every review-gate site has its as-is-or-rider decision recorded in the worksheet.

PHASE 4 — The cluster — one coordinated window

When: One low-activity week (Decision 5) ¦ Who: All hands: IT + CS, Clinicians, Epic, Training, HR owners ¦ Do not start until: Phases 1–3 closed; train pre-copy caught up (delta small); fix-list staffing committed for the same week; root nav updates scheduled for move days

CS, Clinicians, Epic, emr, train, and HR — six as-is 1:1 moves in a single window. They point at each other constantly — train→Epic 21 links, Epic→CS 16, train→HR 13, Epic→HR 10. Moved separately, each move re-breaks links in sites already fixed; moved together, there is exactly one fix pass. (The planned merges — Clinicians into CS, emr into Epic — are Phase 8 items.)

Pre-work — running since Phase 2

Changed 7/29:  Training (259 GB, busy live site) no longer copies inside the window. Background bulk copy starts during Phases 2–3, batched by library/folder, big batches overnight and weekends to keep daytime throttling off the other waves; incremental passes re-run as the delta shrinks. By this window, train's 'move' is only the final small delta — which keeps its freeze short. Be deliberate with this one: it is the site users will feel.

The week's shape

☐  Days 1–2 — the small four: Clinicians, emr, Epic, CS, in ascending inbound order. Identical as-is moves, no merge coordination — each site's copy verified before the next starts.

☐  Days 2–3 — train cutover, then HR. train: freeze, final incremental delta, verify, stub — short window thanks to the pre-copy. HR is the heaviest inbound target in the tenant (72 links from train, Committees, Epic, root); it goes when the team is warmed up, not first.

☐  Every move day: root Quick Launch entries for that site repointed the same day — the classic home page stays the working front door throughout.

☐  Days 3–5 — the batched fix pass: all six inbound lists worked as one queue (200 links total). Pages/lists first. 134 are sharing links to regenerate; 92 sit inside documents — triage by the Decision 2 policy, owners take their own site's documents.

Note (7/29 review):  Six zzRootBackup copies land in this same window — confirm ShareGate capacity/timing before committing to the week. The train pre-copy pattern helps; consider pre-staging the backups of the small four the week before.

Close the phase when

☐  All six worksheet rows Complete; combined re-scan of the six old URLs shows nothing live outside accepted document breakage.

☐  One quiet week of helpdesk tickets on the four new sites.

PHASE 5 — Root content out — as-is

When: After Phase 4, before any swap date is committed ¦ Who: IT + All Provider Meetings owner (Decision 6) ¦ Do not start until: Decision 6 made (destination site named). Does NOT wait on the Document Hub.

The root site's own libraries do not survive the swap in place — whatever is still on the root when it swaps goes to the archive URL with it. This phase empties the root of content people actually use. Like everything else, content moves AS-IS to standalone site(s) now; Document Hub routing is Phase 8.

Steps

☐  Relocate All Provider Meetings as-is to its own standalone site (Decision 6 names it — e.g. /sites/ProviderMeetings). The single most-linked content in the tenant (317 links), with new uploads weekly — coordinate the cutover date with the meeting owners and freeze the old library the same day.

☐  Relocate the remaining root libraries as-is — COVID19 Workflows + Resources (107 links), SiteAssets and page images (media referenced by pages that already moved), misc. libraries per the worksheet's Central Park row. One 'root content' site is fine; keep library structure unchanged.

Note (7/29 review):  Root content gets the same discipline: back it up before it's touched or relocated, not just the subsites.

☐  Work the Phase-5 fix list: analysis/fix-lists/wave5-links-to-root-libraries.csv — 607 links tenant-wide now pointing at content with a new home. Same triage order: nav, pages/lists, then documents by policy.

☐  Set the entire classic root read-only. From here to the swap, the old intranet is a museum: browsable, patched to point at new locations, accepting nothing new.

Phase 5b — retired (7/29)

Changed 7/29:  IT & HIM turned out to be 35 GB after July's backup cleanup, not 1.19 TB — and it now moves FIRST, renamed IT, as Pilot A in Phase 1 (Gary, 7/29). Everything that survived of 5b — the old-subsite deletion before the swap, the recycle-bin purge and storage re-baseline, the HIM records-retention sign-off, the %26 encoding hazard on the legacy URL — rides with that pilot. Nothing IT-related remains in this phase.

Close the phase when

☐  Root libraries are empty or frozen, their content live at destinations, the 607-link list worked to policy.

☐  A full-tenant scanner run finds no live links to root libraries outside accepted document breakage.

PHASE 6 — Cutover — buffer window, swap, hub

When: 3–4 week buffer (recommended) + swap day + same-day hub setup ¦ Who: SharePoint admin (swap + hub); IT for verification; comms owner ¦ Do not start until: Phases 1–5 closed. New home page final. Swap pre-flight passed.

Buffer window (3–4 weeks recommended)

The buffer is not idle time — it is the only stub coverage the Phase 4–5 sites (the highest-traffic ones) will ever get, because every stub dies at the swap. Weeks of buffer = weeks of bookmark retraining for HR, train, Epic, CS users. Shorter is possible; the cost is paid in post-swap 404 tickets.

☐  Fix lists at zero (or at documented, accepted exceptions). Full-tenant scanner run archived as the 'before' record.

☐  Rider inventory. List everything still under the root — should be only the two deprecated meeting workspaces plus any review-gate site explicitly accepted as a rider. The old /IT&HIM should be long gone (moved as Pilot A in Phase 1, old copy deleted). Anything on this list changes URL on swap day; confirm each one is meant to.

Note (7/29 review):  The swap archives the WHOLE root collection including subsites (learn.microsoft.com/en-us/sharepoint/modern-root-site — Limitations). Per plan: zero leftover subsites by swap day. This is exactly why zzRootBackup matters — anything riding to the archive is Microsoft's process, not ours.

☐  Pre-flight, both sites (classic root AND the staging new-home site) — any failure blocks the swap:

# Publishing feature history on the classic root — must return nothing

Get-PnPFeature -Scope Site | ? DisplayName -like "*Publishing*"

# Hub / Group / lock state — IsHubSite false, GroupId empty, LockState Unlock

Get-SPOSite https://whallc.sharepoint.com | Select IsHubSite, GroupId, LockState

Get-SPOSite https://whallc.sharepoint.com/sites/<NewHome> | Select IsHubSite, GroupId, LockState

☐  No eDiscovery/legal hold on either site (Purview); nothing — including recycle-bin entries — at the chosen archive URL.

☐  Do NOT register the new home as a hub yet. Hub status on either site makes the swap fail. Confirmed: the root can be a hub after the swap (Invoke-SPOSiteSwap doc). Don't associate Comm Sites to Intranet-Sandbox until after cutover ('duplicate values' error — see the 7/29 notes' sources).

Note (7/29 review):  Discuss Monday (D-D): interim hub on the current root for search/nav before cutover — then disassociate + unregister before the swap, re-register the new root after. Flag: classic hub nav renders only on modern pages, and the classic root HOME page is exactly where users would look for it. Our new sites are modern, so they'd benefit; the old front door wouldn't.

☐  Comms out: date, time, 'the address stays the same, the site will look new', search may lag a few days — and old subsite addresses (whallc.sharepoint.com/HR etc.) stop working entirely at the swap: update bookmarks NOW while the stubs still forward.

Swap day

Invoke-SPOSiteSwap `

-SourceUrl  https://whallc.sharepoint.com/sites/<NewHome> `

-TargetUrl  https://whallc.sharepoint.com `

-ArchiveUrl https://whallc.sharepoint.com/sites/ClassicRootArchive

☐  Run off-hours. The swap takes minutes; search re-indexing takes days — expected, announced, not an incident.

☐  Verify: new home loads at whallc.sharepoint.com; old root + riders intact at the archive URL; retire the staging URL from circulation.

Same day — hub + home site

Register-SPOHubSite https://whallc.sharepoint.com -Principals $null

Set-SPOHomeSite   -HomeSiteUrl https://whallc.sharepoint.com

☐  Restrict who can associate sites to the hub (Principals / admin center) — IT only.

☐  Set-SPOHomeSite enables the app-bar global nav and news rollup; propagation can take hours — run it swap day, not the morning after.

Associate the sites

# one line per migrated site, scriptable from the worksheet inventory:

Add-SPOHubSiteAssociation -Site https://whallc.sharepoint.com/sites/HR -HubSite https://whallc.sharepoint.com

☐  Association is logical only — no URLs change, no content moves; each site picks up the hub theme, shared nav, hub search scope and news rollup immediately.

☐  Leave 'sync hub permissions' OFF — the sites' unique permissions are deliberate.

Build the hub navigation

☐  Build from the worksheet's Target Destination column — the new architecture — not from the old Quick Launch. Two levels, three max; audience targeting for role-specific links.

☐  Rebuild the home page's quick-links web parts against /sites/ URLs; replace or retire the old People Search add-in (EmployeeDirectoryPro) — it does not carry over.

Note (7/29 review):  Suggestion (D-F): postpone People Search — treat it as its own small project rather than a swap-day dependency.

☐  Final scanner run against the new home + hub nav: zero classic references closes the phase.

PHASE 7 — The tail — 60 to 90 days

When: From cutover to project close ¦ Who: IT + helpdesk ¦ Do not start until: Phase 6 verified stable

☐  The stubs are already gone — they rode to the archive with the old root at the swap, and old subsite paths now 404. From here the safety net is helpdesk tickets: the detector for links the scan could never see — bookmarks, emailed links, Teams chats, print. Triage weekly; fix the target, not the symptom.

Note (7/29 review):  Fine as-is: losing the stubs here is a UX/bookmark issue only — retention was already handled by zzRootBackup long before this point.

☐  At 30 days: review the ticket trend. Quiet = on schedule. Noisy on one site = its fix list gets a second pass, and its owner re-sends the new URL to their audience.

☐  At 60–90 days: the classic archive site (old root + riders, including the now-dead stubs) stays read-only, unlinked, retained per records policy. Confirm retention with HIM/compliance and record it in the Decision Log.

☐  Close out: final full-tenant scan archived next to the original 7/17 baseline; worksheet Status column all Complete; lessons-learned notes into the governance Decision Log.

Note (7/29 review):  Decision Log: build it once this plan is finalized. Document Hub libraries can be scaffolded now — content waits for Phase 8.

PHASE 8 — Transformation — deferred until the Document Hub is ready

When: Post-cutover, own timeline, no deadline pressure ¦ Who: Governance team + site owners + IT ¦ Do not start until: Document Hub live in production; Phase 7 closed; team capacity

Everything the original dispositions wanted — merges, Teams conversions, Document Hub routing — happens here, deliberately deferred so the migration never waited on the Hub. Each item is a small, planned content move between MODERN sites, run with the same core loop discipline: scan the source's inbound links first, move, fix, verify. These are second moves, so each one re-breaks links just fixed during migration — the price of moving as-is first, kept small because these are the low-inbound sites.

The queue (worksheet 'Proposed Disposition' column is the source of truth)

☐  Merges: Clinicians → CS (Clinical Services), emr → Epic (Clinical Systems), Safety + QI + hipaa → one Compliance site. Content consolidates into the surviving site; the vacated site gets a redirect and retires.

☐  Committee sites → Teams channels: Committees umbrella, Int, Comp, Fin, Ops, PFTC, RecruitmentCommittee, HIM Committee, IS. Files land in each committee's Teams channel library; Comp and Fin to private channels.

☐  Document Hub routing: Forms, CRL, ClinicianResources → Hub libraries with folder-based auto-tagging; CtrlAltDelight_Newsletter → future issues as News posts, back-catalog archived; All Provider Meetings + COVID libraries → Hub pages/libraries per the Hub architecture doc.

☐  Help Desk portal: collapse to a page on the IT site, or retire in favor of the help desk tool.

Note (7/29 review):  Same discipline, lighter version: standard ShareGate copy before each merge/move — these are modern-to-modern, not classic-template risk.

Rules that keep this phase safe

☐  One transformation at a time; re-run the link scanner scoped to the source site before each move — links have accumulated since migration.

☐  Every vacated URL gets a redirect, same as Phase 1–5 stubs.

☐  No transformation starts while its target is mid-change (e.g. don't merge into CS while CS is being restructured for the Hub).

Appendix — the fix lists and the numbers

analysis/fix-lists/ contains one CSV per migrating site (inbound-to-<site>.csv): every tenant location holding a link TO that site, with source site, item type (Navigation / Page / ListItem / Document), exact item path, confidence, an IsSharingLink flag, and the matched URL. Sorted so nav and pages float to the top — the fast, high-visibility fixes. wave5-links-to-root-libraries.csv (607 rows) drives Phase 5. _per-site-workload-master.csv is the one-row-per-site rollup behind the worksheet columns and the inventory table in this document.

Numbers reference: 2,485 at-risk occurrences = 1,622 self (ShareGate) + 246 inbound (fix lists) + 607 root-library (Phase 5) + 10 malformed. 296 sharing links regenerate; 738 distinct links exist only inside documents (Decision 2). Verified against the raw 7/17 scan on 7/20.

Size reference: 2026-07-27_RootSubSite-SizeAudit.xlsx — 36 subsites totaling 456 GB; top five (train, Clinicians, HR, IT&HIM, Safety) hold 95% of it; 26 sites are under 1 GB. Root row (1,380 GB) is collection-level and pending a recycle-bin purge + re-audit after the IT&HIM cleanup.