## 2026 OB
OB Ultrasound - Worflow and Protocol Requests
Date of Request | Who made request | Issue/Concern/Request | Solution | Owner | Resolution Plan/Date | Date Completed
2026-04-08 | Dr. Smrtka | If EPIC does not have the functionality to enter this information, how can this information be documented so the patient’s dating information is correct in EPIC? | ongoing training of staff members entering data 09/16/26
2026-04-06 | Dr. Lannon | Can we remove first trimester cord insertion abnormalities from reporting?
2026-04-09 | Dr. Sienas | FU for cord insertio. Suggested language " a possible marginal cord insertion is noted. Attention to cord insertion at second trimester anatomy scan recommended" | additional discussion among MFMs 9/16/26 | Ashlie
2026-04-09 | Dr. Sienas | 2VC in 1st tri: a two vessel cord is identified. This has been associated with the increased risk of structural anomalies and growth restriction. For this reason, a detailed second trimester anatomy ultrasound is recommended." | additional discussion among MFMs 9/16/26 | Ashlie
2026-04-08 | Dr. Tronnes | AFI: borderline low normal AFI. Should we have a canned comment in the impression section for low normal AFI? | additional discussion among MFMs 9/16/26 | Ashlie
2026-04-15 | Chandry | vanishing twins- can we incorporate recommedation for GC for these patients to discuss genetic screening options? | patients with a vanishing twin may receive NATERA NIPT (drawn only at NWP). These patients should be offered GC visit to discuss screening options. | Ashlie | Communiation was relayed at May 7th APM by Ashlie, and via email to sono's May 17 by Larissa | May 17th
2026-05-14 | Dr. Sienas | (CPC finding) Can this text be changed to just say NIPT - we aren't typically doing the other ones now: This finding has been weakly associated with trisomy 18; however when seen in isolation does not substantially increase the risk for aneuploidy, and in the setting of prior low-risk aneuploidy screening (e.g. NIPT, sequential screening, or quad screen) is considered a normal variant. they are going to see those in the report and ask why they didn't have them or can they have them | verify w/ GC workgroup 09/16/26; sent VP data to AT 09/18/26//LAG | Ashlie
2026-05-20 | Larissa | Currently there is not a routine twin anatomy quick report for 14 0/7- 14 6/7 weeks. We will need to build this quick report and add the CPT code 76810 to coding VP section. | LG- work on mock up- send to LW | Larissa
2026-05-20 | Larissa | Update the associated CPT code for KCL procedures to 59897 (billing states that this is an unlisted code- coder needing to add pricing and notes in the charge line) | non-imaging codes -dropped by clinician performing |  | no additional work needed | 2026-09-16
2026-05-20 | Larissa | Missing codes in VP- need to be added: CVS- 59015 and 59015-59 Amnio - 59000 and 59000-59 | non-imaging codes -dropped by clinician performing |  | no additional work needed | 2026-09-16
2026-06-15 | Larissa/Abby | autopopulate 'normal' maternal structures in first tri report
2026-07-15 | Julia | Add ICD-10 code for retained products of conception "O73.0" to the RPOC GYN quick report
2026-07-15 | Chandry | Multiple quick reports that are for "reeval growth" in detailed exams are populating "CRL" into the Previous U/S field under the Dating section for singletons - this needs deleted
2026-07-16 | Chandry | Revise canned comment for "No fetal pole seen" that says "Consider a follow up ultrasound in 1-2 weeks as clinically indicated to reevaluate viability. (If no YS recommend follow-up in 2 weeks, if yolk sac recommend follow-up in 11 days or more. ACOG Practice Bulletin 150, 2015)." Instead of consider follow up ultrasound in 1-2 weeks, change this to 11-14 days.
2026-07-22 | Joley Powell/Larissa | the maxilla and mandible do not auto launch with the following detailed anatomy quick reports: AMA, obesity, EIF, CPC, 2VC. The maxilla and mandible do auto launch with detailed anatomy quick reports: normal, normal with subops, UTD
2026-08-07 | Chandry | add a drop down option in red text for "elevated" when umbilical artery Dopplers are 95th %ile or greater
2026-08-07 | Chandry | When selecting "Invasive Procedures" as the exam type - it only has data fields in the body of the report for 2nd trimester invasive procedures: Need options to document "assessment" instead of "general assesment" that is used in the second trimester for cases we are doing CVS produres
2026-07-17 | Laura | can we also have the completed 76805 and 76111 reports default to "No additional follow-up for the anatomic survey is recommended." as the follow-up.
2026-09-23 | Danielle | add 2VC to OB communication plan. Dr. Tronnes, how should we proceed?
2026-10-05 | Lisa W | in the first trimester quick reports, the add-in reports for bleeding in early pregnancy (QR- I), pelvic pain (QR- J) and abd pain (QR- K) were just adding the indication and code. Since the codes are obsolete now, are those quick reports still needed? | confirmed with Ashlie- we can omit | Lisa | ok to remove | 2026-10-13
2026-10-05 | Lisa W | Can we remove all the reports that have ZZ in the name from all exam types now? |  | Lisa | ok to remove per Larissa | 2026-10-13
2026-10-05 | Lisa W | Can we remove [test] from the add-in maternal structures in 2nd/3rd tri |  | Lisa | ok to remove per Larissa | 2026-10-13
2026-10-08 | Laura Sienas | Can we add a canned comment for 'Incidental BPP score of _____'?

## 2026 GYN
GYN Ultrasound - Worflow and Protocol Requests
Date of Request | Who made request | Issue/Concern/Request | Solution | Owner | Resolution Plan/Date | Date Completed
2026-05-20 | Larissa | Create and add additional adenomyosis descriptors to the myometrium drop down -globular appearing; asymetrical thickening of anterior/posterior myometrium; cycsts within the myometrium; hyperechoic islands withing myometrium; fan shaped shadowing; irregular junctional zone; echogenic subendometrial lines and buds; translesional vascularity. Update the adenomyosis canned comment in impression drop down: 'The myometrial tissue texture appears heterogeneous with findings as noted above. These findings are suggestive of adenomyosis.' | Larissa sent proposed changes to applications 09/24/26//LAG | Larissa |  | 2026-10-04
2026-05-20 | Larissa | VP report>fibroid findings drop down> add 'submocosal' standalone to the submucosal options. Keep existing submucosal drop down options | keep < 50% and >50%, adding submocosal as third option ticket submitted to applications 09/24/26 //LAG | Lisa |  | 2026-10-04
2026-05-20 | Larissa | Modify endo polyp reporting. Body of report: can we re-name the title of the Polyp(s) field to 'Endometiral lesion'? Can we update the canned comment 'This is suggestive of an endometrial polyp though other lesion cannot be excluded' | Unable to change the title; though other endometrial lesion cannot be excluded ticket sumbitted to applications 09/24/26//LAG | Larissa | 2026-09-16 | 2026-10-04
2026-05-20 | Sonographer | Can we add a canned comment about endometrial hyperplasia in GYN VP report?
2026-05-20 | Sonographer | SIS prep instructions vs GYN prep instructions. Do SIS patients receive the same bladder prep instructions as the GYN pelvic US? Patients have complained about having to follow bladder prep for SIS appointments. Can we explore different prep instructions for SIS?
2026-07-23 | Melinda | can we add Nuva Ring to contraception options?
2026-08-19 | Brandi | incorporate scheduling pessary removal/reinsertion for GYN US patients; modify GYN US order to include 'pessary present' option to prompt PS team
2025-09-17 | Chandry | Can we add "surgically absent" to the uterus drop down options for patients with total and partial hysterectomies
2026-10-06 | Larissa | FIGO fibroid mapping- how can we introduce this reporting process? Is this aligned with the fibroid mapping on the GE machines that will map to VP with VP software update?
2026-10-06 | Larissa | Introduce deep endometriosis protocols- reporting
2026-10-07 | Danielle | create 3D comment under uterine anomaly- this was our way to communicate to billing if we are intending to bill for 3D | email sent to IT 10/7/26, ticket ##RE-133961## | LAG | Lisa plans to complete task week of 10/12 | 2026-10-13
2026-10-07 | Danielle | Can we add a comment about the endometrium to the polyp QR? | Brandi approves: "The endometrial echo measures ... and is not uniform." being added to the polyp QR. Ticket ##RE-133998## | LAG | 10/13:waiting on clarification from Larissa - LW

## Master
Ultrasound - Worflow and Protocol Requests
Date of Request | Who made request | Issue/Concern/Request | Solution | Owner | Resolution Plan/Date | Date Completed